## Version Control
Version # | Implemented | Revision | Approved | Approval | Reason
| By | Date | By | Date
1 | Madelyn Cruz Tan | 2025-10-12 | Tan Yong Huat | 2025-10-12 | Initial Risk Management Log Draft

## Risk Management Log
No. | Risk Type | Risk Description | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Unable to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delayed deployment |  | Mitigate | Conduct regular progress reviews and set internal milestones to detect slippage early.
2 | Hardware | Hardware failure e.g., Hard Drive corrupted | Low | High |  | 4 | Loss of data or development progress |  | Mitigate | Maintain version control and off-site backups to restore work quickly.
3 | Software | Feature creep | Medium | High |  | 7 | Delays and overextension of scope |  | Avoid | Implement change control and require sponsor approval for new features.
4 | Communication | Updates to code not communicated to every member | High | Medium |  | 7 | Merge conflicts and inconsistent documentation |  | Avoid | Use shared repositories and weekly sync meetings to align updates.
5 | Resource | Staff Unavailability | Medium | Medium |  | 6 | Reduced productivity and delayed deliverables |  | Transfer | Redistribute workload or bring in temporary support when necessary.
6 | Software | System not meeting requirements | Low | High |  | 5 | Additional debugging and rework required |  | Avoid | Conduct user acceptance testing (UAT) early and review requirements frequently.
7 | Software | Poor code design (e.g., high coupling) | Low | Medium |  | 3 | Difficult to modify or scale system |  | Avoid | Adopt modular architecture and enforce peer reviews.
8 | Communication | Miscommunication of requirements from stakeholders | Low | High |  | 6 | Rework or redesign of system |  | Avoid | Hold validation sessions with stakeholders before finalizing features.
9 | External | Sensitive data being leaked or hacked | Low | High |  | 6 | Loss of user trust and reputational damage |  | Avoid | Implement encryption, secure APIs, and periodic vulnerability scans.
10 | Communication | Incomplete Documentation | Low | Low |  | 2 | Knowledge gaps and maintenance difficulties |  | Avoid | Maintain living documentation and assign review responsibility per sprint.
11 | Software | Inconsistent Programming Style | Low | Medium |  | 3 | Code readability and maintainability issues |  | Avoid | Adopt a team coding standard and automated linting tools.
12 | External | Changes in government data policy or API access | Medium | High |  | 7 | Integration features may stop functioning |  | Mitigate | Monitor policy updates and design flexible API abstraction layers.
13 | Security | User impersonation or spam reports | Low | High |  | 5 | System integrity compromised |  | Mitigate | Use 2FA and CAPTCHA during user registration and reporting.
14 | AI Functionality | AI misclassifies or fails to detect duplicate reports | Medium | Medium |  | 6 | Reduced user trust and administrative inefficiency |  | Mitigate | Periodically retrain the AI model and allow manual overrides.
15 | Compliance | Non-compliance with PDPA or Smart Nation security guidelines | Low | High |  | 6 | Potential legal and reputational consequences |  | Avoid | Consult PDPA compliance checklist and implement proper data handling procedures.
16 | Project Management | Inaccurate cost or schedule estimation | Medium | Medium |  | 5 | Overrun of time or resources |  | Mitigate | Use progressive estimation and contingency buffers.
17 | Testing | Inadequate test coverage or late defect discovery | Medium | High |  | 8 | Deployment delays or post-release failures |  | Mitigate | Integrate unit and system testing early in the development cycle.

## Top 10 Risks
No. | Risk Type | Risk Description | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Unable to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delayed deployment |  | Mitigate | Conduct regular progress reviews and set internal milestones to detect slippage early.
2 | Testing | Inadequate test coverage or late defect discovery | Medium | High |  | 8 | Deployment delays or post-release failures |  | Mitigate | Integrate unit and system testing early in the development cycle.
3 | Software | Feature creep | Medium | High |  | 7 | Delays and overextension of scope |  | Avoid | Implement change control and require sponsor approval for new features.
4 | Communication | Updates to code not communicated to every member | High | Medium |  | 7 | Merge conflicts and inconsistent documentation |  | Avoid | Use shared repositories and weekly sync meetings to align updates.
5 | External | Changes in government data policy or API access | Medium | High |  | 7 | Integration features may stop functioning |  | Mitigate | Monitor policy updates and design flexible API abstraction layers.
6 | Resource | Staff Unavailability | Medium | Medium |  | 6 | Reduced productivity and delayed deliverables |  | Transfer | Redistribute workload or bring in temporary support when necessary.
7 | Communication | Miscommunication of requirements from stakeholders | Low | High |  | 6 | Rework or redesign of system |  | Avoid | Hold validation sessions with stakeholders before finalizing features.
8 | External | Sensitive data being leaked or hacked | Low | High |  | 6 | Loss of user trust and reputational damage |  | Avoid | Implement encryption, secure APIs, and periodic vulnerability scans.
9 | AI Functionality | AI misclassifies or fails to detect duplicate reports | Medium | Medium |  | 6 | Reduced user trust and administrative inefficiency |  | Mitigate | Periodically retrain the AI model and allow manual overrides.
10 | Compliance | Non-compliance with PDPA or Smart Nation security guidelines | Low | High |  | 6 | Potential legal and reputational consequences |  | Avoid | Consult PDPA compliance checklist and implement proper data handling procedures.

## Matrix
Impact | High | 1.Hardware failure e.g., Hard Drive corrupted 2. System not meeting requirements 3. Misunderstanding/Miscommunication of requirements from stakeholders 4. Sensitive data being leaked/hacked 5. User impersonation or spam reports 6. Non-compliance with PDPA or Smart Nation security guidelines | 1. Unable to meet Project Deadline 2. Feature creep 3. Changes in government data policy or API access 4. Inadequate test coverage or late defect discovery
| Medium | 1. Poor code design (e.g. high coupling) 2. Inconsistent Programming Style | 1. Staff Unavailability 2. AI misclassifies or fails to detect duplicate reports 3. Inaccurate cost or schedule estimation | 1. Updates to code not communicated to every group member
| Low | 1. Incomplete Documentation
|  | Low | Medium | High
Probability